## Sheet1
KPIs
Project count by type of poject | pie | Summary page
active project | KPI
Total project completed till now | KPI
Active Client | KPI
Project cost provided | KPI
Actual cost estimation | KPI
Man power required in hrs | KPI
Man power provided in hrs | KPI
Active issue | KPI
Project by phase | Stack bar chart
Project detail table | Table

## Data
Sr No | ProjectOwner | Project | ProjectType | ProjectPhase | Milestone | Client | ProjectStatus | StartDate | FinishDate | WorkHoursProvided | WorkHoursEstimated | WorkHourVariance | WorkHourUtilized | ProjectCost | ProjectCostEstimated | ProjectCostVariance | ActiveIssues | Year | Month | MonthYear
1 | Stephen Langdon | Object-Based Holistic Product | New Development | Requirement Gathering | Requirement Confirm | Gusikowski and Sons | Active | 2021-06-01 | 2021-09-14 | 840 | 772.8 | 67.2 | 814.8 | 58800 | 54096 | 4704 | 4 | 2021 | Sep | Sep-2021
2 | Joshua Bell | Synchronised Incremental Info-Mediaries | Maintenance | Estimation | Requirement Analysis | O'Reilly, Kub and Schroeder | Active | 2021-05-15 | 2021-08-23 | 800 | 736 | 64 | 776 | 56000 | 51520 | 4480 | 1 | 2021 | Aug | Aug-2021
3 | Kylie Jones | Visionary Static Capability | Feature Requirement | Planning | ManHours planning | Miller, Von and Tremblay | Active | 2021-04-01 | 2021-06-25 | 680 | 625.6 | 54.4 | 659.6 | 47600 | 43792 | 3808 | 4 | 2021 | Jun | Jun-2021
4 | Victor Underwood | Synchronised System-Worthy Interface | New Development | Execution | Proto Release | Zemlak Inc | Active | 2021-01-05 | 2021-08-21 | 1824 | 2188.8 | -364.8 | 1769.28 | 127680 | 153216 | -25536 | 3 | 2021 | Aug | Aug-2021
5 | Joan Sutherland | Synergized Heuristic Systemengine | Feature Requirement | Planning | Infrastructure Analysis | Nikolaus-Koss | Active | 2021-03-15 | 2021-06-29 | 848 | 780.16 | 67.84 | 822.56 | 59360 | 54611.2 | 4748.8 | 1 | 2021 | Jun | Jun-2021
6 | Alexandra Hamilton | Implemented National Encoding | Feature Requirement | Execution | Architecture Design | Collins Group | Active | 2021-01-05 | 2021-07-27 | 1624 | 1948.8 | -324.8 | 1575.28 | 113680 | 136416 | -22736 | 4 | 2021 | Jul | Jul-2021
7 | Keith Hart | Synergistic Systematic Solution | New Development | Execution | Sample code Test | Padberg Ltd | Active | 2021-01-05 | 2021-07-13 | 1512 | 1814.4 | -302.4 | 1466.64 | 105840 | 127008 | -21168 | 2 | 2021 | Jul | Jul-2021
8 | Joan Edmunds | Secured Incremental Moderator | Feature Requirement | Execution | Code review | Hickle, Hintz and Gutmann | Active | 2021-01-05 | 2021-07-07 | 1464 | 1346.88 | 117.12 | 1420.08 | 102480 | 94281.6 | 8198.4 | 1 | 2021 | Jul | Jul-2021
9 | Julia Stewart | Progressive Zerodefect Utilisation | Maintenance | Execution | Integration | Sanford-Schroeder | Active | 2021-01-05 | 2021-09-21 | 2072 | 2486.4 | -414.4 | 2009.84 | 145040 | 174048 | -29008 | 4 | 2021 | Sep | Sep-2021
10 | Victor Duncan | Compatible Cohesive Functionalities | Feature Requirement | Estimation | Manpower Analysis | Quitzon-Von | Active | 2021-05-25 | 2021-09-25 | 984 | 905.28 | 78.72 | 954.48 | 68880 | 63369.6 | 5510.4 | 2 | 2021 | Sep | Sep-2021
11 | Nicholas Springer | Quality-Focused Context-Sensitive Frame | Feature Requirement | Execution | UI Development | Brakus, Ortiz and Baumbach | Active | 2021-01-05 | 2021-08-17 | 1792 | 2150.4 | -358.4 | 1738.24 | 125440 | 150528 | -25088 | 3 | 2021 | Aug | Aug-2021
12 | Sue Fisher | Digitized Multi-State Portal | New Development | Planning | Sprint Planning | Legros Inc | Active | 2021-03-21 | 2021-07-01 | 816 | 750.72 | 65.28 | 791.52 | 57120 | 52550.4 | 4569.6 | 1 | 2021 | Jul | Jul-2021
13 | Chloe Walsh | Public-Key Demand-Driven Frame | Feature Requirement | Closing | UAT Test | Champlin, Bauch and Tremblay | Active | 2021-01-05 | 2021-06-12 | 1264 | 1162.88 | 101.12 | 1226.08 | 88480 | 81401.6 | 7078.4 | 1 | 2021 | Jun | Jun-2021
14 | Jonathan Dickens | Switchable Dynamic Knowledgebase | Feature Requirement | Requirement Gathering | Internal Review | Wiza, Denesik and Kilback | Active | 2021-06-06 | 2021-12-31 | 1664 | 1996.8 | -332.8 | 1614.08 | 116480 | 139776 | -23296 | 3 | 2021 | Dec | Dec-2021
15 | Felicity Vance | Cross-Platform Stable Archive | New Development | Closing | Release | Ortiz, Lehner and Sauer | Active | 2021-01-05 | 2021-06-15 | 1288 | 1184.96 | 103.04 | 1249.36 | 90160 | 82947.2 | 7212.8 | 1 | 2021 | Jun | Jun-2021
16 | Nicholas Roberts | Up-Sized Interactive Extranet | Feature Requirement | Execution | Smoke Test | Hammes Ltd | Active | 2021-01-05 | 2021-09-15 | 2024 | 2428.8 | -404.8 | 1963.28 | 141680 | 170016 | -28336 | 2 | 2021 | Sep | Sep-2021
17 | Victoria Stewart | Cross-Platform Multimedia Software | Feature Requirement | Execution | Database Test | Schmeler, Satterfield and Kohler | Active | 2021-01-05 | 2021-07-30 | 1648 | 1977.6 | -329.6 | 1598.56 | 115360 | 138432 | -23072 | 4 | 2021 | Jul | Jul-2021
18 | Thomas Wright | Innovative Full-Range Flexibility | Maintenance | Execution | System Test | Runolfsson-Veum | Active | 2021-01-05 | 2021-10-10 | 2224 | 2668.8 | -444.8 | 2157.28 | 155680 | 186816 | -31136 | 2 | 2021 | Oct | Oct-2021
19 | Angela Bailey | Horizontal Motivating Framework | Feature Requirement | Estimation | Project Value Estimation | Batz LLC | Active | 2021-05-10 | 2021-11-13 | 1496 | 1376.32 | 119.68 | 1451.12 | 104720 | 96342.4 | 8377.6 | 3 | 2021 | Nov | Nov-2021
20 | Grace Nolan | De-Engineered Empowering Interface | New Development | Requirement Gathering | Requirement Clarification | Walsh-Heidenreich | Active | 2021-05-30 | 2021-08-15 | 616 | 566.72 | 49.28 | 597.52 | 43120 | 39670.4 | 3449.6 | 2 | 2021 | Aug | Aug-2021

## Issues
Sr No | IssueType | AssignTo | DueDate | Priority | ActiveIssues | ProjectOwner | Project
1 | Client Issue | Mark | 2021-09-07 | P3 | 4 | Stephen Langdon | Object-Based Holistic Product
2 | Development Issue | Bunny | 2021-08-16 | P1 | 1 | Joshua Bell | Synchronised Incremental Info-Mediaries
3 | Project Manager Issue | Jhon | 2021-06-18 | P2 | 4 | Kylie Jones | Visionary Static Capability
4 | Technology issue | Jack | 2021-08-14 | P4 | 3 | Victor Underwood | Synchronised System-Worthy Interface
5 | Client Issue | Mark | 2021-06-22 | P3 | 1 | Joan Sutherland | Synergized Heuristic Systemengine
6 | Development Issue | Bunny | 2021-07-20 | P1 | 4 | Alexandra Hamilton | Implemented National Encoding
7 | Project Manager Issue | Jhon | 2021-07-06 | P2 | 2 | Keith Hart | Synergistic Systematic Solution
8 | Technology issue | Jack | 2021-06-30 | P4 | 1 | Joan Edmunds | Secured Incremental Moderator
9 | Client Issue | Mark | 2021-09-14 | P3 | 4 | Julia Stewart | Progressive Zerodefect Utilisation
10 | Development Issue | Bunny | 2021-09-18 | P1 | 2 | Victor Duncan | Compatible Cohesive Functionalities
11 | Project Manager Issue | Jhon | 2021-08-10 | P2 | 3 | Nicholas Springer | Quality-Focused Context-Sensitive Frame
12 | Technology issue | Jack | 2021-06-24 | P4 | 1 | Sue Fisher | Digitized Multi-State Portal
13 | Client Issue | Mark | 2021-06-05 | P3 | 1 | Chloe Walsh | Public-Key Demand-Driven Frame
14 | Development Issue | Bunny | 2021-12-24 | P1 | 3 | Jonathan Dickens | Switchable Dynamic Knowledgebase
15 | Project Manager Issue | Jhon | 2021-06-08 | P2 | 1 | Felicity Vance | Cross-Platform Stable Archive
16 | Technology issue | Jack | 2021-09-08 | P4 | 2 | Nicholas Roberts | Up-Sized Interactive Extranet
17 | Client Issue | Mark | 2021-07-23 | P3 | 4 | Victoria Stewart | Cross-Platform Multimedia Software
18 | Development Issue | Bunny | 2021-10-03 | P1 | 2 | Thomas Wright | Innovative Full-Range Flexibility
19 | Project Manager Issue | Jhon | 2021-11-06 | P2 | 3 | Angela Bailey | Horizontal Motivating Framework
20 | Technology issue | Jack | 2021-08-08 | P4 | 2 | Grace Nolan | De-Engineered Empowering Interface

## Sheet2
Sr No | ProjectOwner | Project | ProjectType | ProjectPhase | Milestone | Client | ProjectStatus | StartDate | FinishDate | WorkHoursProvided | WorkHoursEstimated | WorkHourVariance | WorkHourUtilized | ProjectCost | ProjectCostEstimated | ProjectCostVariance | ActiveIssues | Year | Month | MonthYear
1 | Stephen Langdon | Object-Based Holistic Product | New Development | Requirement Gathering | Requirement Confirm | Gusikowski and Sons | Active | 2021-06-01 | 2021-09-14 | 840 | 772.8 | 67.2 | 814.8 | 58800 | 54096 | 4704 | 4 | 2021 | Sep | Sep-2021
2 | Joshua Bell | Synchronised Incremental Info-Mediaries | Maintenance | Estimation | Requirement Analysis | O'Reilly, Kub and Schroeder | Active | 2021-05-15 | 2021-08-23 | 800 | 736 | 64 | 776 | 56000 | 51520 | 4480 | 1 | 2021 | Aug | Aug-2021
3 | Kylie Jones | Visionary Static Capability | Feature Requirement | Planning | ManHours planning | Miller, Von and Tremblay | Active | 2021-04-01 | 2021-06-25 | 680 | 625.6 | 54.4 | 659.6 | 47600 | 43792 | 3808 | 4 | 2021 | Jun | Jun-2021
4 | Victor Underwood | Synchronised System-Worthy Interface | New Development | Execution | Proto Release | Zemlak Inc | Active | 2021-01-05 | 2021-08-21 | 1824 | 2188.8 | -364.8 | 1769.28 | 127680 | 153216 | -25536 | 3 | 2021 | Aug | Aug-2021
5 | Joan Sutherland | Synergized Heuristic Systemengine | Feature Requirement | Planning | Infrastructure Analysis | Nikolaus-Koss | Active | 2021-03-15 | 2021-06-29 | 848 | 780.16 | 67.84 | 822.56 | 59360 | 54611.2 | 4748.8 | 1 | 2021 | Jun | Jun-2021
6 | Alexandra Hamilton | Implemented National Encoding | Feature Requirement | Execution | Architecture Design | Collins Group | Active | 2021-01-05 | 2021-07-27 | 1624 | 1948.8 | -324.8 | 1575.28 | 113680 | 136416 | -22736 | 4 | 2021 | Jul | Jul-2021
7 | Keith Hart | Synergistic Systematic Solution | New Development | Execution | Sample code Test | Padberg Ltd | Active | 2021-01-05 | 2021-07-13 | 1512 | 1814.4 | -302.4 | 1466.64 | 105840 | 127008 | -21168 | 2 | 2021 | Jul | Jul-2021
8 | Joan Edmunds | Secured Incremental Moderator | Feature Requirement | Execution | Code review | Hickle, Hintz and Gutmann | Active | 2021-01-05 | 2021-07-07 | 1464 | 1346.88 | 117.12 | 1420.08 | 102480 | 94281.6 | 8198.4 | 1 | 2021 | Jul | Jul-2021
9 | Julia Stewart | Progressive Zerodefect Utilisation | Maintenance | Execution | Integration | Sanford-Schroeder | Active | 2021-01-05 | 2021-09-21 | 2072 | 2486.4 | -414.4 | 2009.84 | 145040 | 174048 | -29008 | 4 | 2021 | Sep | Sep-2021
10 | Victor Duncan | Compatible Cohesive Functionalities | Feature Requirement | Estimation | Manpower Analysis | Quitzon-Von | Active | 2021-05-25 | 2021-09-25 | 984 | 905.28 | 78.72 | 954.48 | 68880 | 63369.6 | 5510.4 | 2 | 2021 | Sep | Sep-2021
11 | Nicholas Springer | Quality-Focused Context-Sensitive Frame | Feature Requirement | Execution | UI Development | Brakus, Ortiz and Baumbach | Active | 2021-01-05 | 2021-08-17 | 1792 | 2150.4 | -358.4 | 1738.24 | 125440 | 150528 | -25088 | 3 | 2021 | Aug | Aug-2021
12 | Sue Fisher | Digitized Multi-State Portal | New Development | Planning | Sprint Planning | Legros Inc | Active | 2021-03-21 | 2021-07-01 | 816 | 750.72 | 65.28 | 791.52 | 57120 | 52550.4 | 4569.6 | 1 | 2021 | Jul | Jul-2021
13 | Chloe Walsh | Public-Key Demand-Driven Frame | Feature Requirement | Closing | UAT Test | Champlin, Bauch and Tremblay | Active | 2021-01-05 | 2021-06-12 | 1264 | 1162.88 | 101.12 | 1226.08 | 88480 | 81401.6 | 7078.4 | 1 | 2021 | Jun | Jun-2021
14 | Jonathan Dickens | Switchable Dynamic Knowledgebase | Feature Requirement | Requirement Gathering | Internal Review | Wiza, Denesik and Kilback | Active | 2021-06-06 | 2021-12-31 | 1664 | 1996.8 | -332.8 | 1614.08 | 116480 | 139776 | -23296 | 3 | 2021 | Dec | Dec-2021
15 | Felicity Vance | Cross-Platform Stable Archive | New Development | Closing | Release | Ortiz, Lehner and Sauer | Active | 2021-01-05 | 2021-06-15 | 1288 | 1184.96 | 103.04 | 1249.36 | 90160 | 82947.2 | 7212.8 | 1 | 2021 | Jun | Jun-2021
16 | Nicholas Roberts | Up-Sized Interactive Extranet | Feature Requirement | Execution | Smoke Test | Hammes Ltd | Active | 2021-01-05 | 2021-09-15 | 2024 | 2428.8 | -404.8 | 1963.28 | 141680 | 170016 | -28336 | 2 | 2021 | Sep | Sep-2021
17 | Victoria Stewart | Cross-Platform Multimedia Software | Feature Requirement | Execution | Database Test | Schmeler, Satterfield and Kohler | Active | 2021-01-05 | 2021-07-30 | 1648 | 1977.6 | -329.6 | 1598.56 | 115360 | 138432 | -23072 | 4 | 2021 | Jul | Jul-2021
18 | Thomas Wright | Innovative Full-Range Flexibility | Maintenance | Execution | System Test | Runolfsson-Veum | Active | 2021-01-05 | 2021-10-10 | 2224 | 2668.8 | -444.8 | 2157.28 | 155680 | 186816 | -31136 | 2 | 2021 | Oct | Oct-2021
19 | Angela Bailey | Horizontal Motivating Framework | Feature Requirement | Estimation | Project Value Estimation | Batz LLC | Active | 2021-05-10 | 2021-11-13 | 1496 | 1376.32 | 119.68 | 1451.12 | 104720 | 96342.4 | 8377.6 | 3 | 2021 | Nov | Nov-2021
20 | Grace Nolan | De-Engineered Empowering Interface | New Development | Requirement Gathering | Requirement Clarification | Walsh-Heidenreich | Active | 2021-05-30 | 2021-08-15 | 616 | 566.72 | 49.28 | 597.52 | 43120 | 39670.4 | 3449.6 | 2 | 2021 | Aug | Aug-2021

## Sheet3
Sr No | IssueType | AssignTo | DueDate | Priority | ActiveIssues | ProjectOwner | Project
1 | Client Issue | Mark | 2021-09-07 | P3 | 4 | Stephen Langdon | Object-Based Holistic Product
2 | Development Issue | Bunny | 2021-08-16 | P1 | 1 | Joshua Bell | Synchronised Incremental Info-Mediaries
3 | Project Manager Issue | Jhon | 2021-06-18 | P2 | 4 | Kylie Jones | Visionary Static Capability
4 | Technology issue | Jack | 2021-08-14 | P4 | 3 | Victor Underwood | Synchronised System-Worthy Interface
5 | Client Issue | Mark | 2021-06-22 | P3 | 1 | Joan Sutherland | Synergized Heuristic Systemengine
6 | Development Issue | Bunny | 2021-07-20 | P1 | 4 | Alexandra Hamilton | Implemented National Encoding
7 | Project Manager Issue | Jhon | 2021-07-06 | P2 | 2 | Keith Hart | Synergistic Systematic Solution
8 | Technology issue | Jack | 2021-06-30 | P4 | 1 | Joan Edmunds | Secured Incremental Moderator
9 | Client Issue | Mark | 2021-09-14 | P3 | 4 | Julia Stewart | Progressive Zerodefect Utilisation
10 | Development Issue | Bunny | 2021-09-18 | P1 | 2 | Victor Duncan | Compatible Cohesive Functionalities
11 | Project Manager Issue | Jhon | 2021-08-10 | P2 | 3 | Nicholas Springer | Quality-Focused Context-Sensitive Frame
12 | Technology issue | Jack | 2021-06-24 | P4 | 1 | Sue Fisher | Digitized Multi-State Portal
13 | Client Issue | Mark | 2021-06-05 | P3 | 1 | Chloe Walsh | Public-Key Demand-Driven Frame
14 | Development Issue | Bunny | 2021-12-24 | P1 | 3 | Jonathan Dickens | Switchable Dynamic Knowledgebase
15 | Project Manager Issue | Jhon | 2021-06-08 | P2 | 1 | Felicity Vance | Cross-Platform Stable Archive
16 | Technology issue | Jack | 2021-09-08 | P4 | 2 | Nicholas Roberts | Up-Sized Interactive Extranet
17 | Client Issue | Mark | 2021-07-23 | P3 | 4 | Victoria Stewart | Cross-Platform Multimedia Software
18 | Development Issue | Bunny | 2021-10-03 | P1 | 2 | Thomas Wright | Innovative Full-Range Flexibility
19 | Project Manager Issue | Jhon | 2021-11-06 | P2 | 3 | Angela Bailey | Horizontal Motivating Framework
20 | Technology issue | Jack | 2021-08-08 | P4 | 2 | Grace Nolan | De-Engineered Empowering Interface
Formulas:
DueDate = VLOOKUP([Project],Sheet2!C:J,8,0)-7

## Data Defination
Sr No | ProjectOwner | Project | ProjectPhase | Client | ProjectStatus | StartDate | FinishDate | Requirement | Estimation | Planning | Execution | Closing | WorkHoursProvided | WorkHourUtilized | Year | Month | MonthYear | Milestone | IssueType | AssignTo | Priority
|  |  | Requirement Gathering |  | Active | Date | Date | Date | Date | Date | Date | Date | [6 empty] | Client Issue | Mark | P3
|  |  | Estimation | [15 empty] | Development Issue | Bunny | P1
|  |  | Planning |  | Closed | [13 empty] | Project Manager Issue | Jhon | P2
|  |  | Development | [15 empty] | Technology issue | Jack | P4
QA
Closed